Education, Health & Care (EHC) Needs Assessment Improvement Plan

The purpose of this plan is primarily to address the issues identified within the LGSCO letter.  It will be incorporated into the wider SEND Partnership Improvement Plan

| Outcome to be achieved (What do we need to do) | Progress Milestones (How will we know we are making progress) | Senior Responsible Officer (SRO) | Timescale | BRAG (Blue/Red/Amber/Green) rating | Accountability & Monitoring |
| --- | --- | --- | --- | --- | --- |
| Recruit agency workers for the short-term to increase ability to meet the demand for new EHC assessment requests | - Agencies found able to provide Educational Psychologists (EPs) and EHC Plan writers - Additional agency staffing sourced and in place - An extra 330 assessments completed every 3 months | Deputy Director, Resources & Transformation | January 2026 February 2026 April-June 2026 onwards | Amber | Children’s Scrutiny Corporate Leadership Team (CLT) Children & Families Senior Leadership Team (C&FSLT) |
| Recruit additional new staff permanently in the Educational Psychology Service (EPS) and the SEN Statutory Assessment & Provision (SENSAP) Team to meet demand for new EHC assessment requests | - New posts established and approved for more Educational Psychologists (including Assistant EPs) and additional EHC Plan writers and Case Officers in SENSAP Team - Recruitment process underway - New staff successfully in post - An extra 110 assessments able to be completed every month | Deputy Director, Learning | January 2026 February/ March 2026 June 2026 July 2026 | Amber | Children’s Scrutiny CLT C&FSLT |
| Recruit a short-term specialist team of agency workers to complete delayed EHC assessments by no later than June 2027 | - Agency found able to provide enough educational psychology and EHC Plan writers - Agency workers recruited and in place - Circa 400 EHC assessments completed in quarter 1 - Circa 850 EHC assessments completed by quarter 2 - Circa 1300 EHC assessments completed by quarter 3 - Circa 1750 EHC assessments completed by quarter 4 - All outstanding delayed EHC assessments completed within 18 months of contract being established | Deputy Director, Resources & Transformation | January 2026 February 2026 May 2026 August 2026 November 2026 February 2027 June 2027 | Amber | Children’s Scrutiny CLT C&FSLT |
| Improve the compliance rates and increase the percentage of EHC assessments completed within 20 weeks in line with National average within 3 years | - 20% of EHC assessments completed in 20 weeks - 37% of EHC assessment compliance completed in 20 weeks - 49% of EHC assessments completed in 20 weeks (based on 2025 published data) | Chief Officer, SEND | December 2026 December 2027 December 2028 | Monitoring to start from January 2026 | Children’s Scrutiny SEND & AP Partnership Board Health & Well-Being Board CLT C&FSLT |
| Improve communication and response times with parents/carers | - Parent/carer communication to be acknowledged within 3 working days - Full responses to be provided to parents/carers within 10 working days. - Options to be explored to develop a “multi-chat” response team to respond to on-line parental queries in real time - Increased capacity to improve communication responsiveness in place. | Chief Officer, SEND Deputy Director, Transformation & Resources | January 2026 January 2026 February 2026 March 2026 | Amber | SEND & AP Partnership Board CLT C&FSLT |
| Establish a clear “fast-track” route for EHC assessments with clear and published criteria on exceptional & urgent cases, with the aim for “fast-track” EHC assessments to be completed within 16 weeks | - “Fast-track” criteria to be developed and agreed - Approach to deliver “fast-track” assessments for exceptional/urgent circumstances to be in place - “Fast-Track” assessments aim to be completed within 16 weeks | Chief Officer, SEND | January 2026 April 2026 May 2026 | Green | C&FSLT |

Blue – Action Complete

Red – Action not on track to be completed in timescale

Amber – Risk of action not being completed in timescale

Green – Action on track to be completed in timescale